## Instructions
Honeyguide’s proposed annual work plan for WMAs must contain the following key columns; 1. Major annual goals/Milestones –these should align with the strategic plan. What are the key, critical outcomes your WMA needs to achieve this year? The Goal should be a short statement, using as few words as possible. These goals lead into and frame the key tasks described in following column. Needs to be one goal per row. Consider numbering each annual milestone. You might also use a separate column for numbering milestones, for easier filtering. 2. Key tasks/Activities/Task-lists –what initiatives or actions are required to achieve those goals? This column identifies the key sets of initiatives or actions aimed at achieving the annual goals laid out in the previous. These form the heart of the work plan, as these activities and their respective targets guide all actions as required to achieve the goals. Usually multiple activities to accomplish the annual milestone. Only put a summarized task and not detailed steps for the task. The detailed subtasks should be managed separately in the project management/implementation tool such as zoho, trello or another separate detailed spreadsheet. You can put additional notes in the notes column if the activity description is too long. Consider numbering each activity in relation to its annual milestone number e.g. activities for milestone 1 could be numbered 1.1, 1.2, 1.3 etc. These can be used to reference activities, or milestones in the annual budget also while reporting. As well as in other detailed work plans if needed. 3. Expected Outcomes – what are the intended results of the actions being taken? Usually links with the annual milestone/goal. It can be helpful to think through what change the key task will bring and clarify how that change allows you to achieve your overarching goal. For example, if a key task is to develop a communications strategy, it is useful to think through how the outcome will contribute towards achieving the goal of strengthening the WMA. These outcomes can sometimes be found in existing project level documents such as grant proposals. Needs to be one outcome sentence per goal. Can be a compound sentence which comprises several outcomes caused by the activities in the milestone. 4. Time-frames/Timelines - when do things need to happen by? Can be specified by quarters (Q1 to Q4) or by months (Jan to Dec). For future implementation reporting, this column can be broken down into 4 (if quarterly) or 12 (if monthly). Can be one overall expected timeframe for the entire milestone or broken down per activities listed. 5. Annual targets, deliverables or outputs – what monitoring metrics will you use to verify delivery? Needs to be a bulleted list of outputs or deliverables expected to prove completion of the work and ultimately prove progress towards the organization’s strategic goals. Other WMA documents such as grant proposals, strategic plans or monitoring plans may already have some of these metrics clearly defined. These deliverables can also be used together with financial reports as outputs to external funders or donors of the activities as part of justifying the completion of the agreed work. Ideally one or more bullets for each of the listed activities in the milestone. In excel, press ‘ALT+ENTER’ to make a new line and consider using an asterisk ‘*’ or minus ‘-‘ symbol for each bullet. 6. Notes – Any additional notes and comments for the goal, milestones or activities (can be blank if no additional notes needed). It is helpful to use this column to explain activity description or intended outputs where it was not clearly stated in the previous columns (activity or deliverables columns).
Additional optional columns; • Thematic area – a column to categorize your annual goals/milestones into certain programmatic themes eg protection, management, governance, community livelihoods and awareness, tourism/enterprise development etc. This helps when you want to filter your programs or themes. • Responsible or lead - who is accountable for different deliverables? Usually initials of a management staff responsible for the supervising implementation of the specific task. Does not have to all be assigned to the WMA manager but for instance tourism activities might be assigned to a tourism officer. It is a best practice to have only one lead. This column can also be used to indicate responsible/supporting organization for the activity. • Resources – This column highlights the resources required to complete all activities in the respective annual goal/milestone. Can be split into several columns such as; o Budget/Activity costs – How much is needed to complete all activities under this annual goal/milestone? Can be a total of all activities under the annual goal or a breakdown for each of the listed activity items. Consider having a separate spreadsheet for a detailed budget that has referenced budget lines that matches the activity numbers in the work plan (see in the example spreadsheet). Also note that some budget cost items (especially the recurring ones such as staff salaries) might not be directly linked to activities in the work plan. o Available budget/shortfall – How much funds are already available for the planned activities under the respective milestone? or can show the shortfall instead. o Expected donor – Who or what organization (if any) is expected to fund the activity or the entire milestone
Useful additional columns for future work plan progress reporting; • Status – This column is the basic 'dashboard' status tool for a quick highlight of work plan progress reporting, which is changed and updated according to progress against the Key Tasks (or Activities) and its respective Annual Targets (outputs or deliverables). This can be updated monthly, or quarterly, as preferred by management. The column has both a color coding and letter explanation. Proposed status indicators includes; o Not started = activity not begun but on track as not yet scheduled to start (clear); o In progress = activity begun and progressing fully according to schedule (blue); o Slightly off track (or minor issues) = progress slower than anticipated or there was a slight delay in relation to the schedule (yellow); o Delayed (or major issues) = progress significantly impeded and requiring attention (red); o Complete = Activity fully complete, target met (green). o Periodic updates notes – Space to comment on progress in terms of each annual goal (and its activities), and to explain the status of the key task in relation to its annual target. This basically explains the indicated status from the “Status” column. It is particularly helpful to provide notes for key tasks where the status dashboard shows the tasks are off track or seriously delayed in order to explain the reasons for the delay and what steps will be taken to address it. Consider adding a new column for each reporting period, for instance (Q1 update, Q2 update, Q3 update and Q4 update) if reporting quarterly or otherwise as needed.

## Instructions 2 (hidden)
Instructions Overview This document provides a template for an organization-wide annual work plan. The objective of this format is to fit an entire annual work plan and work tracking system within a simple and easily digestible format. This is useful for senior management, in terms of condensing more detailed work plans into a set of summary goals, key tasks, and annual targets, as well as for reporting using a 'dashboard' system to the board or key funders. Using this format requires, above all, that managers think critically about their major organizational priorities, key tasks and targets, and that they frame and present these in precise and clear language. The text presented on the next worksheet ('Sample Work Plan') provides an example of how an organization-wide work plan can be presented, while the third sheet presents a work plan template into which you can enter your own text to make this plan useful to your organization.
Column A: Goals This column provides the backbone for the organization's overall work plan - the major goals or 'pillars' of an organization's work and should be based on your strategic plan or business plan. The Goal should be a short statement, using as few words as possible. These goals lead into and frame the key tasks described in Column C.
Column C: Key Tasks This column identifies the key sets of initiatives or actions aimed at achieving the Goals laid out in Column A. These form the heart of the work plan, as these activities and their respective targets guide all actions as required to achieve the goals.
Column D: Status This column is the basic 'dashboard' status tool, which is changed and updated according to progress against the Key Tasks (Column C) and its respective Annual Targets (Column H). This can be updated monthly, or quarterly, as preferred by management. The column has both a color coding and letter explanation: Not started = activity not begun but on track as not yet scheduled to start (clear); In progress = activity begun and progressing fully according to schedule (blue); Slightly off track = progress slower than anticipated or delayed in relation to the schedule (yellow); Delayed = progress significantly impeded and requiring attention (red); Complete = Activity fully complete, target met (green).
Column E: Timeframe This column provides clear timeframes for each key task described in Column C. Timeframes can be set as either quarterly, if you do not yet know the exact timing, or monthly if you do.
Column F: Lead This column records the responsible person leading on each key task. Although multiple people may be involved in a key task, it is worth identifying one person who is accountable, acting as the point person and ensuring that deadlines are met.
Column G: Expected Outcomes This column provides the intended results from each key task or set of activities. It can be helpful to think through what change the key task will bring and clarify how that change allows you to achieve your overarching goal. For example, if a key task is to develop a communications strategy, it is useful to think through how the outcome will contribute towards achieving the goal of strengthening the organization. These outcomes can sometimes be found in existing project level documents such as grant proposals.
Column H: Annual Targets This column provides the monitoring metrics that can be used to measure progress against the key tasks, and ultimately against the organization’s strategic goals. Other project documents such as grant proposals or monitoring plans may already have some of these metrics clearly defined.
Column I: Resources This column highlights the funding available and the source of funding. It can be used to flag where there is a funding gap for some planned activities.
Column J: Notes Here the organization has space to comment on progress in terms of each key task, and to explain the status of the key task in relation to its annual target. It is particularly helpful to provide notes for key tasks where the status dashboard shows the tasks are off track or seriously delayed in order to explain the reasons for the delay and what steps will be taken to address it.

## Sample Work Plan 1 (hidden)
WILDLIFE MANAGEMENT AREA
2018 Annual Work Plan
Goals | S/N | Key Tasks | Status | Timeframe | Lead | Expected Outcomes | Annual Targets | Resources | Notes
1.0 Strengthen community land tenure in six target villages. | 1.1 | Facilitate participatory village land use planning, boundary demarcation, and development of village by-laws in six villages. | Delayed | Q2-Q3 | AT | Clarity on all village boundaries and legal basis for enforcement of community land use zones | * Digital LUPs in place in 6 villages * Approval of village by-laws by Village Assembly and submission to District Council | USAID ($10,000) | Timeline contingent on ability to resolve outstanding village boundary conflicts.
| 1.2 | Carry out six training workshops with Village Councils and Land Committees. | Slightly off track | March | AT | Established clear procedures for implementation and enforcement of village by-laws and land use rules, resulting in enforcement of grazing and other land use zones. |  | USAID ($10,000) | Ongoing boundary conflicts in villages D and F impacted by politics. Resolution not expected until after government elections in Dec 2018. Will be a priority for Q1-2 2019
2.0 Increase community revenue from tourism joint ventures | 2.1 | Facilitate joint venture agreements for construction of ecolodge in Enkiteng conservancy. | In progress | February | SR | Enkiteng conservancy JV agreement in place and base revenue paid | Enkiteng conservancy receives $15,000 in base revenue | Investor funded ($55,000) | Discussions around JV agreement progressing smoothly. Some friction with construction manager - support Enkiteng in building better relationship
| 2.2 | Faciliate the resolution of village boundary conflicts. | Complete | Q2 | PT | Boundary conflict resolved so conservancies can enter into contracts with investors. | A new grazing agreement between Osikiria and Orkejo conservancies. | Community paid ($4,000)
| 2.3 | Establish partnership with Conservation Business Advisors to provide customized training to field staff on joint venture negotiation and contract structure. | Not started | Q4 | SR | Improved staff capacity to facilitate community tourism joint ventures. | * Revenue agreement in place * Osikiria and Orkejo conservancies each receive at least $5000 in conservancy revenue |  | No budget currently allocated. Awaiting outcome of USAID grant, and will need to seek additional funding
3.0 Grow membership base of Community Based Organisations (CBOs) representing areas conserved by indigenous people and local communities | 3.1 | Consolidate and document Community Based Organisation membership levels. | Slightly off track | July | PT | Clarity about members' advocacy responsibilities depending on their level of membership | Membership levels handbook | Oxfam ($3,500) | Levels depend on matrix assessing CBO's connectedness to government and other influential stakeholders, as well as severity of land rights infringements local community represented by CBO is facing
| 3.2 | Carry out campaign to recruit all Piniandan community lands rights CBOs. | Not started | Q4 | BN | Increased ability to advocate at a national level about community land rights and a coordinated voice for ICCA conservation of land and resources. | 80% of ICCA CBOS are members (target of 184 organisations) | Not funded yet | 65% of ICCA CBOs are already members (150/ 230 organisations)
4.0 Organizational Development - Improve financial sustainability and resourcing through effective fundraising. Strengthen internal communications capacity and develop clear communications strategy. | 4.1 | Implement business plan. | Not started | Q4 | AT | 10% of core costs being generating through service provision payments by land rights CBOs. | $20,000 secured through service provision payments (10% of core costs of $200,000) | TNC ($15,000) | ICCA CBOs have received free support for the previous three years. Information sharing visit regarding the importance of cost recovery planned to all districts during Q2, however resistance is still anticipated. Develop plan to address anticipated objections
| 4.2 | Develop Communications Strategy to identify communications goals, target audiences, messages and channels of communication. | In progress | Q3 | SR | Increased interest in membership and improved ability to carry out advocacy at a national level. | Communications Strategy | TNC ($5,000) | New communications manager currently being recruited and expected to start in March 2016

## Sample Workplan
Wildlife Management Area
2020 Annual Work Plan (Version 1.0)
SN | Annual goal [Milestones] | Thematic area | Activity [Tasklists] | Expected Outcomes | Timeline | Lead | Annual Targets and deliverables | Expected Donor | Cost of Activity | Available Budget | Status | Notes and additional comments | Q1 Update | Q2 Update | Q3 Update | Q4 Update
2.1 | Develop a capable WMA management towards sustainability through coaching and training. | Management | 2.1.1 Prepare the WMA management for MAT level 4 (+Management tool box) 2.1.2 Ongoing WMA leadership trainnings, formal coachings and feedback meetings. 2.1.3 Procure and maintain existing equipment+infrastructure to support WMA management functions 2.1.4 Review the WMA Business plan and 5-year Conservation Action Plan (CAP) | General the WMA management is moving towards sustainability (Decisions, Revenue & expenses mgt) | Q1-Q4 | SS | * Management toolbox (incl. report templates, asset registry, appraisal system, mgt flow chart). * Training+Coaching checklist * Monthly+Quarterly mgt meetings + coaching sessions * WMA succession plan for Honeyguide's Driver+Ops+AP staff * New Suzuki carry for office supplies, store, vehicle workshop, fuel storage station, solar repairs, Mgt/staff housing * Updated WMA business plan * New CAP |  |  |  | Not started | ..in Mgt coaching, incl.. how they can manage existing infrastructures. + Projects development fund + new investor contracts and relations
2.2 | Develop and test a WMA governance capacity building and monitoring framework. | Governance | 2.2.1 SAGE next steps (+internal governance assesment tool to measure SAGE improvement) 2.2.2 WMA governance capacity building trainings (Principles->Roles->Sust.->technical trainings) | Governance capacity building framework developed, tested, documented and can be replicated in other WMA | Q1-Q4 | SS | * Simplified internal governace assessment tool to be used by the WMA to track improvement. * WMA governance capacity building checklist * WMA governance capacity building reports of trainings. |  |  |  | In progress | ...in collaboration with UCRT. Consider investing first in the new AA members and newly elected village leaders.
2.3 | Improve tourism experience in the WMA through infrastructures, services, marketting and investor affairs | Tourism | 2.3.1 Plan for underperfoming properties and get new investor in WMA 2.3.2 Improve accessibilty in the WMA 2.3.3 Develop WMA marketing strategy and tools 2.3.4 Improve Customer service in the WMA (relations and service) 2.3.5 the WMA cultural boma | WMA business plan targets achieved for 2020 | Q1+Q4 | MM | * Plan for underperfoming properties in WMA (Boundary hill, elephant, ecoscience and Naitolia) * New tourism property in the WMA * New game-drive roads, maintained existing roads, cement road up sunset, Navigation app, TNP access gate, gates improvements, airfield banda, gravel airfield?? * WMA marketting strategy, Website update, waterhide complete, brochures, tourist feedback system, WMA story narrative for tourists * WMA tourism customer care training for VGS * Updated investor contracts * Improved cultural boma experience |  |  |  | Slightly off track | 2.3.1 incl. Boundary hill, elephant, ecoscience and Naitolia 2.3.2 incl. roads new+repair+sunset, Nav app, TNP access gate, airfield murram?+waiting banda 2.3.4 incl updated investor contracts (incentive based)
2.4 | Improve local attitudes or the WMA communities and awareness about WMA, wildlife and conservation | Awareness | 2.4.1 Develop and test the WMA communication strategy + monitoring framework 2.4.2 Show the WMA awareness film to all 8 villages and all schools 2.4.3 Develop specific targetted WMA awareness materials (Annual report poster, sust. pillars films ...) | the WMA has a communication and awareness strategy which incl. awareness monitoring framework | Q1-Q2 | LL | * WMA awareness and communications strategy. * WMA awareness monitoring tool for WMAs * Awareness film on WMA shown to all 8 villages * Film monitoring report |  |  |  | Delayed
2.5 | Improve capacity of WMA to manage AP efficiently and take 100% of antipoaching cost. | Protection | 2.5.1 Review and enforce Antipoaching SOP 2.5.2 Update the WMA long-term anti poaching plan 2.5.3 Develop a stronger informer and inteligence system 2.5.4 Necessary AP equipment (vehicle, …) | the WMA in charge all AP operations (incl. costs) as per long term AP strategy and SOP. | Q1-Q4 | LK | * Qtrly the WMA SOP monitoring, 100% on mandatory and 60% on optional standards by year-end. * Long-term AP plan for the WMA. * Monthly AP strategic plans with SMART. * Intelligence manual, intelligence training and training reports, and established intelligence networks * 100% of the protection cost covered by WMA. * New AP car |  |  |  | Complete
2.6 | Develop long term future plan for WMA crop protection where the program is run without external support. | HWC | 2.6.1 WMA+communities funding 100% of HWC toolkits+monitoring costs. 2.6.2 HWC monitoring and reporting by WMA and communities. 2.6.3 Develop future HWC plan for the WMA which includes AA and villages. | WMA community understand and values the HWC initiatives and agree to take on toolkit purchase and monitoring going forward according to the aggreed future program plan. | Q1-Q3 | LM | * HWC toolkits needs assessment * Monthly crop protection reports showing incidents and toolkit usage * Communities and WMA collect and manage all data. * 2020 HWC report showing toolkits contributions, incidents and toolkit usage. * Future HWC plan aggreed by WMA, AA and villages. |  |  |  | In progress | 2.6.1 Incl. Honeyguide support for additional flashlights + back up vehicle.

## Template 1 (hidden)
ORGANIZATION NAME
2018 Annual Work Plan
Goals | S/N | Key Tasks | Status | Timeframe | Lead | Expected Outcomes | Annual Targets | Resources | Notes
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started

## Template
WMA NAME
YYYY Annual Work Plan (Version X.x)
SN | Annual goal [Milestones] | Thematic area | Activities [Key tasks or Tasklists] | Expected Outcomes | Timeline | Lead | Annual Targets and deliverables | Expected Donor | Cost of Activity | Available Budget | Status | Notes and additional comments | Q1 Update | Q2 Update | Q3 Update | Q4 Update
2.1 | [10 empty] | Not started
2.2
2.3
2.4
2.5
2.6